## Sheet1
SUGGESTED REGIONAL MEETING PLANNING SCHEDULE
MEETING NAME:
MEETING DATE: |  | to
IMPORTANT DEADLINES
Abstract Deadline
Advance Registration & Abstracts open on the Web
C&EN Info due to RMP
Final Program in C&EN
Hotel Cut Off Date
Advance Registration Closes
Meeting Start Date
Approximate Planning Time
Prior to Meeting
| Three To Five Years out |  | Contact Regional Board of Directors (BOD) regarding their criteria for selecting a host section
and bid requirements.
Contact ACS Regional Meeting Planner (RMP) for background information, e.g., history of past meetings,
budget templates, suggestions to include in bid.
Contact local Convention & Visitors Bureau
Submit bid information for consideration by deadline established by BOD.
Make presentation to Regional BOD at the next regional meeting
| Two to Three Years out |  | Local Section should appoint General Chair, who should appoint Program Chair(s). General Chair
should appoint remaining committee chairs and hold planning committee meeting to include:
Agenda,
Schedule of session/events,
Resource materials/contracts,
Educational program direction/emphasis and
Deadlines/time frames.
Contact your ACS RMP to assist you in preparing your request for meeting site proposals (RFP),
and to arrange for site inspections, and contract negotiations
Your ACS RMP will contact the local Convention and Visitors Bureau for assistance in finding a
suitable location and to meet with your planning committee.
Your RMP should review all contracts and/or written agreements with conventions centers, hotels,
and/or universities prior to your review and signing. The contract is between the facility and the
Host Section and should be signed by the general chair and an officer of the local section
(usually the treasurer).
General and Program Chairs should attend the ACS Regional Meeting Planning Conference,
preferably two to three years before the regional meeting.
Establish a timeline to include any deadlines in your contracts.
| 18 months to Two years out |  | Review the contract to determine if meeting specifications are still valid.
Exposition Chair should select tabletops or pipe & drape for exposition and prepare an RFP for
decorating companies. (NOTE: If you select tabletop exhibits, request an estimate from the hotel
for providing draped tables, chairs, and waste receptacles also.)
Obtain bids from local decorating companies for both options.
Request a price for poster boards as well.
Send proposal/contract to your RMP to review before signing.
Your RMP is able to assist you with locating companies and contract negotiations. He or she
should review all bids and contracts prior to your signing.
Expo Chair should develop an order form for vendors. NOTE: ACS can process any credit card
transactions for booth space. Ask your RMP for details.
Revise budget based upon current and anticipated expenses. Include travel support for speakers
and any estimated complimentary registrations for speakers, exhibitors, and committee, et al.
Develop marketing timeline and budget and incorporate into meeting budget and master timeline.
Program Chair should select symposia and general session organizers.
Invite keynote speakers.
Set up meeting web site.
Send articles to local sections in your area requesting them to include the information in
their newsletters.
Your RMP will send you contact information for the local section officers in your region so you
can send them articles for their newsletters and ask them to participate.
| One year to 18 Months out |  | Marketing begins in earnest. Decide if you want to participate in a joint ad with the other
regionals being held in the spring or fall. Your RMP will contact you and make the arrangements.
Prepare signs and flyers to announce your meeting at the current year's meeting and at the
two ACS national meetings prior to yours.
Encourage committee members to attend the current year’s meeting to see what they are doing
and to talk with their counterparts to get tips.
Contact Divisions to garner their support via programming or funding.
| One Year out |  | Generate an ad to submit to the current year's program book.
Determine components of marketing plan i.e.; websites, e-mail, mailings, flyers and
ads in C&EN. Publicity/promotional efforts are available in Local Section and Division
publications as well. Develop marketing timeline and budget and incorporate into
meeting budget and master timeline.
Contact company research directors and university department chairs & university PR offices
and ask them to promote the meeting, encourage paper submission, and attendance.
Begin exposition promotion. Your RMP will send you contact information on national ACS
exhibitors in your region to assist in selling booths and/or sponsorships.
Request to be placed on agendas of several divisions to request their participation in the meeting.
Distribute flyers around national meetings and at regional meetings booth. Plan to spend time in
the booth and solicit vendors for your exposition.
10 Months out
Hold committee meeting to review progress.
Refine budget estimates.
Request publicity in newsletters of other Local Sections in region, in nearby regions and/or Divisions
for registration and housing. Include registration estimates in budget.
Submit meeting information to journals other than ACS journals so they will publish the date and
location, and perhaps some details about the meeting.
| 8 months |  | Begin finalizing the programming for your meeting in anticipation of establishing the contents
for the online abstract system, which will open approximately 6 months before the meeting.
Hold committee meeting to check progress.
Refine budget, if necessary.
Four to six weeks before the online abstract program is scheduled to open, your RMP will arrange
for a training session in using the system with selected committee members.
| 6 Months out |  | Once the technical program has been decided, prepare a Call for Papers to be published in
C&EN around the time the abstracts open. Your RMP will assist you in preparing your article
Set closing deadline for abstracts. Deadlines for abstracts are usually8 weeks prior to the meeting.
Contract for AV support.
Hold committee meeting to check progress.
Generate an advance registration form with the assistance of your RMP. When Registration opens
your RMP will send you an advance on proposed income of $5,000.00.
4 to 6 Months out
Contact company research directors and university department chairs and ask them to encourage
paper submission and attendance.
2. Abstract Deadline; Program Committee should review symposia organization and
begin actively recruiting in any areas where papers are needed to fill out general sessions.
Notify regional members that Abstracts and advance registration are open.
Notify regional members of date your Call for Papers publishes in C&EN.
Contact potential exhibitors to remind them of the deadlines for registering to exhibit.
Review your site contract to determine if enough rooms have been contracted for.
Meet with meeting site personnel to verify all arrangements and prices
4 Months to 13 Weeks out
Your RMP will post Advance Registration Form on the Regional Meetings website and link your
Web page to it. We will also develop an online registration form.
The Program Committee should review symposia organization and begin actively recruiting
in any areas where papers are needed to fill out general sessions. Send email bulletins
asking for contributors from the region.
Get printing bids. Your RMP can assist you.
Hold committee meeting to make sure all assignments are underway.
12 Weeks out
Submit Final Program Summary to your RMP for submittal to C&EN.
Send an email blast reminding members of closing dates for abstracts and registration.
9 to 12 Weeks out
Second training session on abstracts program scheduled to show you how to organize the papers.
Request an ad from next year’s meeting to place in your program.
Abstracts close and work begins on organizing the technical program for publication.
4 to 6 Weeks out
Final Program Summary appears in C&EN.
Submit Program to printer with complete instructions for printing & delivery of abstract book.
3 Weeks out
Advance registration closes.
Begin finalizing menus for events. Your RMP can give you estimates on the number of people
who have purchased tickets.
Hold committee meeting to review last-minute details & resolve any problems.
Finalize volunteer, student, and/or convention bureau personnel schedules.
2 Weeks out
Confirm all arrangements with facilities personnel and other contractors.
1 Week out
Hold committee meeting to assure that committee members are
aware of all arrangements and persons to contact in case of on-site problems.
Review budget to date.
Finalize food and beverage orders and notify your hotel/meeting site contact. NOTE: You have
up to 3 business days to amend your order. Once the numbers are set, you can increase but not
decrease food and beverage orders.
ACS requests a check for 80 - 90% of your registration income to be transferred to your bank.
Two day out
Your RMP arrives on-site to prepare registration area and materials.
Hold Pre-con meeting with our RMP and facility staff.
During Meeting
1. With the assistance of your RMP, conduct /manage the Meeting including
educational sessions, special events, social functions and business meetings.
Bill reconciliation, invoice review and gratuities paid
1 month after Meeting
ACS will send you a check for the expenses we have incurred on the master account as soon as
we receive the facility invoice.
ACS will send another check for the bulk of the onsite income collected. Final report will
be available @ 6 months after the meeting. General Chair should prepare a final report, using
the template developed for regional meetings. This information will be submitted to the Regional
BOD with a copy to your Regional Meeting Planner.
2 Months after Meeting
Hold committee meeting and review all committee reports.
4 to 6 Months after Meeting
After receiving all finalized financial and statistical information from your ACS RMP,
edit and finalize the Meeting report. This information will be submitted to the Regional
BOD with a copy to your Regional Meeting Planner.